## Project Timeline
SENIOR PROJECT TIMELINE
PROJECT DETAILS
WHEN | WHAT | WHO | Comments | Position | BASELINE
2013-09-15 | Meet with rep from Villanova to talk about the festival | Powers | Powers get assignments | 14 | 1
2013-09-20 | Request on Calendar |  |  | 20 | 1
2013-09-25 | Announcements | Powers | Add to new Calendar | 10 | 1
2013-09-26 | Transportation -Bus? Cars? | Kaplan | Students will provide their own transportation | -10 | 1
2013-09-30 | Secure NHS/Key club participation |  |  | 30 | 1
2013-10-03 | Design flyers - Pledge to End the word |  |  | -15 | 1
2013-10-01 | RNN/Weekly Information to Parents |  | RNN/Weekly information to parents | 15 | 1
2013-10-07 | Visit homebase |  | Pledge | 10 | 1
2013-10-11 | Recruit volunteers |  | Sign ups | 15 | 1
2013-10-14 | Permission Slips |  | Not needed | -20 | 1
2013-10-15 | Villanova Rep visit school |  | Power to talk about the event and pledge | 20 | 1
2013-10-28 | Confirm Volunteer List - Reminder |  | Remeinders | -15 | 1
2013-11-02 | Special Oympics Festival |  | Take pictures | 15 | 1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.